## Slide 1
MWSC | STRATEGIC PROJECT DEVELOPMENT PROPOSAL
PROJECT FEN RAKKAA
Closing the gap between rufiyaa income and dollar spending
Decision requested: approve a gated MVR 4.5m project against exposure in the tens of millions
Hussain Shaany S2610358 | PTMT9002 Strategic Project Development | 15 August 2026
Notes: Good morning. I am asking this panel to approve Project Fen Rakkaa: a twelve month, MVR 4.5 million project to close the gap between the currency MWSC earns in and the currency it spends in. Five minutes: the problem, the evidence, the options, the value, the risks, then the ask.

## Slide 2
The problem: MWSC earns in MVR and spends in USD
Business Plan 2026 ranks the USD exchange rate crisis as the top corporate challenge (MWSC, 2025a)
PTMT9002 | Project Fen Rakkaa | Hussain Shaany S2610358
2
22.25
MVR per USD
Parallel market rate, 11 Aug 2026. Official peg 15.42. Premium 44% (Adhadhu, 2026; MMA, 2026)
$638m
Gross reserves, Jul 2026
Fell from $1.33bn (Mar) to $717.9m (Apr, 1.4 months import cover) after the $500m sukuk settlement, still falling (MMA, 2026)
~0%
of MWSC revenue in USD
Membranes, pumps, chemicals, pipes and meters all purchased in dollars (MWSC/AGO, 2025)
Structural, not temporary: the premium has widened steadily for two years. Every dollar of imports now costs 44% more rufiyaa than the budget rate assumes.
Chart: 
| 2023 | 2024 | 2025 | Aug 2026
Parallel rate (MVR/USD) | 17.45 | 19 | 20.05 | 22.25
Official peg: 15.42 throughout
Notes: The plan itself names this the top corporate challenge. The parallel rate hit 22.25 on 11 August, a 44 percent premium over the peg. Reserves halved in four months to 1.4 months of import cover. MWSC earns almost nothing in dollars but buys membranes, pumps, chemicals and pipes in dollars. The trend line shows this is structural, not a spike.

## Slide 3
The evidence: the mismatch is already costing MWSC
Audited FY2024 and quarterly disclosures (MWSC/AGO, 2025; MWSC, 2026)
PTMT9002 | Project Fen Rakkaa | Hussain Shaany S2610358
3
FY2025 revenue
MVR 1.37bn, down 13% on 2024 and 62% of the annual goal
FY2025 profit after tax
MVR 146m, down by about a third from 2024
H1 2026 revenue gap
6.4% below budget, widening from 1.9% (Q1) to 10.9% (Q2)
Cash vs receivables
MVR 50.2m cash against MVR 877.8m receivables; MVR 192.1m impairment flagged as a Key Audit Matter
Unmanaged FX exposure
MVR 40–70m
per year
Planning estimate A2: MVR 55m adopted. Derived from 2024 operating costs of MVR 935.3m at a 20–25% dollar-linked share, at realized rates.
Doing nothing is the expensive option: losses are hidden and accumulate as the currency erodes. The exposure register is the first deliverable, so the estimate is replaced by measured values.
Four internal root causes, all actionable: 1. No dollar revenue 2. No treasury controls 3. No FX clauses in contracts 4. No single owner of FX risk
Notes: The cost is visible in the accounts. Revenue fell 13 percent in 2025, profit fell by about a third, and the 2026 budget gap widened from 2 to 11 percent between quarters. Exposure is estimated at 40 to 70 million rufiyaa a year; I adopt 55 as a conservative planning estimate and I am explicit that it is an assumption. That is why the exposure register is the first deliverable. The diagnosis found four internal root causes: no dollar revenue, no treasury controls, no FX clauses, no owner. All four are within MWSC's control.

## Slide 4
Three distinct options, appraised before scoring
Criteria and weightings fixed in advance; scores 1–5 (workings in the proposal, Section 4.1)
PTMT9002 | Project Fen Rakkaa | Hussain Shaany S2610358
4
A. Do Nothing
Baseline
No cost, no disruption
Leaves MVR 40–70m p.a. exposed
Fails every strategic objective
Weighted score
2.45
B. Treasury Fix
Do-minimum
MVR 1.5m, quick to implement
Planning rate, buffer, bulk orders
Revenue mismatch stays unresolved
Weighted score
3.25
C. Fen Rakkaa
Integrated. Recommended
MVR 4.5m, 12 months, 2 gates
Six workstreams: revenue, treasury, procurement, contracts, governance
Only option resolving every root cause
Weighted score
4.30
Sensitivity on the scoring: doubling the cost weight to 30% and cutting strategic fit to 5% still ranks C first (4.00 vs 3.40 and 3.05). The outcome does not depend on the initial weightage.
Option B is retained as the priced fallback if Gate 2 benefits fall short.
Notes: Three genuinely distinct options. A is the baseline: free today, expensive over time. B fixes treasury for 1.5 million but leaves revenue entirely in rufiyaa. C is the integrated project and the only option that addresses all four root causes. The weightings were set before scoring. I stress tested them: even doubling the cost weight and cutting strategic fit, C still ranks first. And B is not discarded; it is the priced fallback if Gate 2 shows benefits below threshold.

## Slide 5
The value: pays back in Year 1, robust to failure
Three-year DCF at 12%; benefits ramp 15% / 35% / 45% of the MVR 55m exposure (Appendix A)
PTMT9002 | Project Fen Rakkaa | Hussain Shaany S2610358
5
33.4m
3-year NPV (MVR)
5.8
Benefit-cost ratio
Year 1
Payback, net cash positive
17%
Benefit realization needed to break even
Chart: 3-year NPV (MVR m) vs benefit realization
| 0% | 20% | 40% | 60% | 80% | 100%
NPV base | -6.9 | 1.2 | 9.2 | 17.3 | 25.4 | 33.4
NPV with costs overrun +2/3 | -4.4 | 3.5 | 11.4 | 19.3 | 27.2 | 35.1
Why the case is honest
Assumption, not fact: benefits rest on the assumed dollar-linked cost share, not published segment data.
Control:
the exposure register replaces the estimate with measured values; the project stays positive at 40% realization even with running costs overrun by two-thirds.
No IRR quoted:
at this cost scale it would imply false precision.
Notes: The financial case. NPV of 33.4 million over three years against 8.1 million total cost, benefit cost ratio 5.8, payback inside Year 1. The number I want the panel to hold is 17 percent: the project breaks even if only 17 percent of the modelled benefits appear. The chart shows NPV stays positive from around 20 percent realization even if running costs overrun by two thirds. I am open about the limitation: benefits rest on an assumed dollar-linked cost share, which is why the exposure register is deliverable one and why I quote no IRR.

## Slide 6
Delivery: twelve months, two gates, a priced fallback
Logframe assigns every result an owner; Gate 2 failure triggers de-scope to Option B
PTMT9002 | Project Fen Rakkaa | Hussain Shaany S2610358
6
Month 0
Month 3
Month 6
Month 9
Month 12
1. Mobilise Q4 2026
Steering committee, champions, USD account
2. Build Q1 2027
Exposure register, dashboard, clause library
3. Scale Q2 2027
Resort outreach, USD billing, bulk import plan
4. Embed Q3 2027
Buffer policy live, divisional KPIs, audit-verified benefits
GATE 1 (Month 6): governance live? Register, dashboard, USD account operational.
GATE 2 (Month 12): benefit realization ≥ 35%? If not, execute the de-scope to Option B at known cost.
Outcome targets by owner: USD billing ≥ 50% of resort clients and ≥ 20% of project revenue by Q2 2027 (GM Business Development) • USD procurement spend down 10–15% by Sep 2027 (Procurement) • USD reserve ≥ 20% of the MVR 30m target by Mar 2027 (CFO) • 100% of new foreign-currency contracts legally reviewed with FX clauses from Q4 2026 (Legal)
Notes: Delivery is deliberately gated because the environment is complex and unpredictable; the design is probe, learn, adjust. Gate 1 at month 6 tests whether governance is actually live. Gate 2 at month 12 tests whether at least 35 percent of projected benefits are real; if not, we fall back to Option B at a known price. Every outcome has a named owner: business development owns USD billing, procurement owns the spend reduction, the CFO owns the buffer, legal owns the clause compliance.

## Slide 7
Principal risks are owned, triggered and priced
Full register in Section 5; any exposure of 12+ escalates to EXCO
PTMT9002 | Project Fen Rakkaa | Hussain Shaany S2610358
7
Risk (cause, event, effect)
Exposure
Owner
Response and trigger
Residual
Peg adjustment forces immediate re-pricing of exposure
15
CFO
Planning band 22.00–22.50; re-baseline within 30 days of announcement
8
Banks ration USD; imports threatened
15
CFO
Multi-bank relationships; USD buffer; escalate to authorities on refusal
8
Resorts reject USD billing; Outcome 1 missed
12
GM, BD
New contracts only; FX-indexed pricing fallback if uptake < 50% by Q1 2027
6
Ministry rejects FX clauses in awards
12
Legal / CFO
FIDIC precedent drafting; ring-fence funds for unhedged exposure
6
The register informs the recommendation: the two highest exposures (peg, USD rationing) are macro events the project cannot prevent, which is exactly why the recommended option builds buffers, bands and fallbacks rather than assuming stability.
Notes: Four principal risks, each stated as cause, event, effect, each with an owner, a trigger and a priced response. The two 15s are macro events: a peg adjustment and dollar rationing. The project cannot prevent them, and that is precisely the argument for it: bands, buffers and fallbacks instead of assumed stability. Residual scores assume the response work is done. Anything scoring 12 or more escalates to EXCO.

## Slide 8
THE DECISION REQUESTED
Approve Option C: Project Fen Rakkaa
MVR 4.5m
Gated spend. 0.3% of revenue against exposure in the tens of millions
12 months
Two gates. Fallback to Option B priced at MVR 1.5m
3 BP26 goals
Delivers USD billing (2.3.4), USD reserve (1.5.10) and contract review (3.3.2) already set by the plan
The causes MWSC can act on are internal. The appraisal shows Option C beats both alternatives and stays positive even if most estimated benefits fail to appear. Failure is defined in advance, measured at the gates, and priced.
Hussain Shaany S2610358 | PTMT9002 | Questions welcome
Notes: The ask: approve Option C. A gated 4.5 million, 0.3 percent of revenue, against exposure in the tens of millions. It delivers three goals the Business Plan has already set. Failure is defined in advance, measured at two gates, and priced through the Option B fallback. I welcome the panel's questions.